## Sheet1
PROJECT BACKLOG
13 | = highest Reference ID number
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 第三方账号登录 | 作为一个作者，我希望能够通过第三方账号登录，以便于更快捷的登录系统，节省时间。 | Initial Feature | Not Done | 3 | 98 |  |  | 2
2 | 1 | 1 | user story | 申请成为作者 | 作为一个作者，我希望能在网站上申请成为作者，以便于我能够在网站上写小说或发布小说 | Initial Feature | Not Done | 1 | 95 |  |  | 1 | 0
3 | 1 | 1 | user story | 发布小说 | 作为一个作者，我希望能够发布自己写的小说，以便于让更多的读者阅读我的小说。 | Initial Feature | Not Done | 3 | 90 |  |  | 3
3 | 1 | 1 | user story | 上传小说的方式 | 作为一个作者，我希望能够通过在线写小说或上传本地文件的方式来上传我的小说，以便于我可以选择上传小说的方式 | Initial Feature | Not Done | 1 | 85 |  |  | 1
4 | 1 | 1 | user story | 写小说简介 | 作为一个作者，我希望能够为自己的小说写简介，以便于吸引读者进行阅读或购买 | Initial Feature | Not Done | 1 | 80 |  |  | 1 | 0
5 | 1 | 1 | user story | 更新小说后续内容 | 作为一个作者，我希望有更新小说后续内容的功能，以便于我能更新我未完结的小说，从而吸引更多的读者阅读 | Initial Feature | Not Done | 2 | 75 |  |  | 2 | 0
6 | 1 | 1 | user story | 审核小说内容 | 作为一个小说管理者，我希望能够有一个查找小说是否含有敏感词或敏感语句的功能，以便于我快速的审核小说是否通过 | Initial Feature | Not Done | 1 | 85 |  |  | 1 | 0
7 | 1 | 1 | user story | 对小说进行分类 | 作为一个作者，我希望有一个对小说进行分类的功能，以便于吸引其他读者进行阅读或购买 | Initial Feature | Not Done | 2 | 70 |  |  | 2 | 0
8 | 1 | 1 | user story | 购买通知 | 作为一个作者，我希望有人购买我的小说时，系统给我发送通知，以便于我了解我的书的阅读或购买情况 | Initial Feature | Not Done | 2 | 65 |  |  | 2 | 0
9 | 1 | 1 | user story | 积分提现 | 作为一个作者，我希望能够提现我的积分。 | Initial Feature | Not Done | 2 | 80 |  |  | 1 | 0
10 | 1 | 1 | user story | 申请推广 | 作为一个作者，我希望能够申请对自己的小说进行推广，以便于我的小说被更多的读者阅读。 | Initial Feature | Not Done | 1 | 70 |  |  | 1
Generate index cards
Note on A4: Luc Segers: This is the highest reference ID number used so far.
Note on A5: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B5: Luc Segers: This is the release where the story will be developped
Note on C5: Luc Segers: This is the sprint where the story will be developped
Note on D5: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F5: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G5: Luc Segers: Type of the story.
Note on H5: Luc Segers: Status of the story
Note on I5: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J5: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L5: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M5: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N5: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O5: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P5: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information